## Worksheet
Project Name | Budget (USD) | Start Date | End Date | Status | Responsible Team | Actual Expenditure (USD) | Variance (%) | Next Review Date
Digital Transformation Initiative | 500,000 | 2023-11-01 | 2024-06-30 | On Track | IT & Operations Team | 425,000 | -15.0% | 2024-03-15
Customer Experience Upgrade | 300,000 | 2024-01-15 | 2024-12-31 | Planning Phase | Marketing & UX Team | 0 | 0.0% | 2024-05-31
Cloud Migration Project | 750,000 | 2023-12-01 | 2025-03-31 | In Progress | Infra & DevOps Team | 480,000 | -36.0% | 2024-11-30
Supply Chain Optimization | 600,000 | 2024-02-15 | 2024-11-30 | At Risk | Logistics & Finance Team | 580,000 | -3.3% | 2024-10-15
Total Projects: |  |  |  | 4 | Total Budget: |  |  | $1,950,000