## Worksheet
Date | Project Name | Budget (USD) | Actual Spend (USD)> | Variance (USD) | Status | Next Milestone | Responsible Team
2023-10-05 | Mobile App Development | 150,000 | 128,450 | +21,550 (Under Budget) | On Track | UI/UX Review by Oct 12 | Development Team
2023-10-05 | Cloud Migration Project | 75,000 | 69,230 | +5,770 (Under Budget) | On Track | Security Audit by Oct 15 | IT Infrastructure Team
2023-10-05 | Customer Portal Upgrade | 90,000 | 94,875 | -4,875 (Over Budget) | At Risk | Phase 2 Approval by Oct 18 | Product Team
2023-10-05 | Marketing Campaign Launch | 40,000 | 37,650 | +2,350 (Under Budget) | On Track | Performance Review by Oct 11 | Marketing Team