## Worksheet
Metric | Current Value | Target Value | Variance (%) | Status
Budget Utilization | 68% | 75% | -9.3% | On Track
Project Timeline | Month 8 of 12 | Month 6 of 12 | +33.3% | Delayed
Cost Variance | $45,000 Over Budget | $50,000 Within Budget | -10% | At Risk
Resource Allocation | 85% | 90% | -5.6% | On Track
Scope Completion | 60% | 80% | -25% | Behind Schedule
Risk Exposure | High (4 out of 10) | Medium (2 out of 10) | +100% | Critical