## Worksheet
Project Name | Status | Budget (USD) | Actual Spend (USD)>% | Progress (%) | Next Milestone | Responsible Team | Action Required
Website Redesign | In Progress | 50,000.00 | 32,450.00 | 65% | Q3 Launch Preview | Marketing & Development Team | Finalize UI/UX approval by 15-May
Customer Onboarding Platform | On Hold | 75,000.00 | 18,900.00 | 32% | Requirements Finalization (Next Week) | Product & Support Team | Reschedule meeting with stakeholders
Data Migration Project | Completed | 40,000.00 | 39,875.00 | 100% | Migrated - Final Review Done | IT Operations Team | Pending post-migration report submission
Mobile App v2.0 | Planning Phase | 120,000.00 | 5,250.00 | 4% | Sprint Planning Meeting (June 1) | Engineering & UX Team | Define feature scope and timeline