## Worksheet
Project Name | Budget (USD) | Actual Spend (USD) | Variance (USD) | Status | Progress (%) | Next Milestone | Responsible Team
Digital Transformation Initiative | 500,000 | 425,000 | +75,000 (Under Budget) | On Track | 85% | Q3 End - System Integration | IT & Strategy Team
Customer Experience Platform Launch | 350,000 | 375,000 | -25,000 (Over Budget) | At Risk | 68% | Mid-October - User Testing | Product & UX Team
Supply Chain Optimization Project | 200,000 | 195,000 | +5,000 (Under Budget) | On Track | 92% | November 15 - Final Review | Operations & Logistics Team
Cloud Migration Program | 600,000 | 582,000 | +18,000 (Under Budget) | On Track | 76% | Q4 - Data Backup Setup | DevOps & Security Team
Total Budget |  |  |  | 1,650,000 | Total Actual Spend | 1,577,000 | Overall Variance: +73,000 (Under Budget)