## Worksheet
Project | Status | Budget (USD) | Actual Spend (USD) | Variance (%) | Forecast | Next Milestone | Owner
Product Launch Q3 | On Track | 250,000 | 215,000 | +14.0% | $275,000 | September 30, 2024 | Emma Rodriguez
Market Expansion (Asia) | At Risk | 400,000 | 325,000 | +18.75% | $395,000 | October 15, 2024 | James Lee
Customer Platform Upgrade | On Track | 300,000 | 295,000 | +1.67% | $315,000 | November 1, 2024 | Sarah Thompson
Cloud Migration Initiative | Delayed | 500,000 | 420,000 | +16.0% | $535,000 | December 15, 2024 | David Chen
AI Integration Pilot | Pending Approval | 150,000 | - | - | $160,000 (Projected) | February 28, 2025 | Lisa Park