## Worksheet
Project Name | Budget (USD) | Actual Spend (USD) | Variance | Status | Start Date | End Date | Progress (%) | Key Risks
Client Onboarding Initiative | 50,000 | 42,500 | +7,500 (Under Budget) | On Track | 2024-03-15 | 2024-06-30 | 85% | Data security compliance delay
Product Launch Phase 2 | 120,000 | 118,200 | +1,800 (Under Budget) | On Track | 2024-04-01 | 2024-09-30 | 78% | Third-party vendor delays
Market Expansion (EU) | 250,000 | 235,000 | +15,000 (Under Budget) | On Track | 2024-05-10 | 2025-03-31 | 65% | Regulatory approval timelines
Internal Process Optimization | 75,000 | 72,400 | +2,600 (Under Budget) | On Track | 2024-03-31 | 2024-11-30 | 90% | Staff resistance to change