## Worksheet
Project Name | Budget (USD) | Actual Spend (USD) | Variance | Status | Progress (%) | Next Milestone
Phase I Development | 500,000 | 425,000 | -75,000 (Under Budget) | On Track | 85% | End of Q2 2024
User Acceptance Testing | 150,000 | 135,000 | -15,000 (Under Budget) | On Track | 78% | Q3 2024
System Deployment | 300,000 | 285,000 | -15,000 (Under Budget) | On Track | 92% | End of Q4 2024
Post-Deployment Support | 100,000 | 105,000 | +5,000 (Over Budget) | On Hold | 25% | Q1 2025