## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependency
Project Initiation | 2024-01-01 | 2024-01-10 | 10 | Jane Doe | Completed
Scope Definition | 2024-01-11 | 2024-01-25 | 15 | John Smith | In Progress | Project Initiation
Risk Assessment | 2024-01-26 | 2024-02-05 | 10 | Alex Kim | Planned | Scope Definition
Resource Planning | 2024-02-06 | 2024-02-15 | 10 | Sarah Lee | Pending
Design Phase | 2024-02-16 | 2024-03-31 | 46 | Mike Chen | Planned | Resource Planning
Development Phase | 2024-04-01 | 2024-06-30 | 91 | Team A | Not Started | Design Phase
Testing & Quality Control | 2024-07-01 | 2024-07-31 | 31 | Lisa Wong | Planned | Development Phase
Project Closure | 2024-08-01 | 2024-08-15 | 15 | Jane Doe | Not Started | Testing & Quality Control