## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Project Manager | Completed
Scope Definition | 2024-01-16 | 2024-02-15 | 30 | Business Analyst | In Progress
Risk Assessment | 2024-02-16 | 2024-03-15 | 30 | Risk Officer | Planned
Resource Planning | 2024-03-16 | 2024-04-15 | 30 | HR & Ops Team | Planned
Design Phase | 2024-04-16 | 2024-06-30 | 75 | Design Team | Scheduled
Development Phase | 2024-07-01 | 2024-11-30 | 150 | Engineering Team | Scheduled
Testing & QA | 2024-12-01 | 2025-01-31 | 60 | QA Team | Planned
Deployment & Go-Live | 2025-02-01 | 2025-02-15 | 15 | IT Operations | Planned
Post-Implementation Review | 2025-02-16 | 2025-03-31 | 45 | Project Manager | Planned