## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-01-01 | 2024-01-07 | 7 | John Smith | Completed
Requirements Gathering | 2024-01-08 | 2024-01-25 | 18 | Sarah Lee | In Progress
Design Phase | 2024-01-26 | 2024-02-15 | 21 | Mike Chen | Planned
Development Phase | 2024-02-16 | 2024-04-15 | 61 | Team A | Not Started
Testing & QA | 2024-04-16 | 2024-05-10 | 35 | Linda Wong | Planned
Deployment & Go-Live | 2024-05-11 | 2024-05-15 | 5 | Robert Park | Not Started
Post-Launch Review | 2024-05-16 | 2024-05-20 | 5 | Project Manager | Planned