## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Manager | On Track
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Business Analyst | On Track
Design Phase | 2024-04-11 | 2024-05-30 | 60 | UX Designer & Dev Lead | On Track
Development | 2024-06-01 | 2024-08-31 | 90 | Software Engineers | On Track
Testing & QA | 2024-09-01 | 2024-10-15 | 45 | QA Team | On Track
Deployment & Go-Live | 2024-10-16 | 2024-10-30 | 15 | Operations Team | Planned
Post-Implementation Review | 2024-11-01 | 2024-11-15 | 15 | Project Manager | Planned