## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 day | Sarah Johnson | Completed
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 days | Michael Chen | In Progress
Design Phase | 2024-03-16 | 2024-04-10 | 35 days | Lisa Thompson | Planned
Development Phase | 2024-04-11 | 2024-06-30 | 81 days | David Park | Not Started
Testing & Quality Assurance | 2024-07-01 | 2024-07-31 | 31 days | Emma Wright | Planned
User Training & Deployment | 2024-08-01 | 2024-08-15 | 15 days | James Lee | Not Started
Project Review & Closure | 2024-08-16 | 2024-08-16 | 1 day | Sarah Johnson | Planned