## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Status | Progress (%)
PMT-001 | Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Smith | Completed | 100
PMT-002 | Scope Definition | 2024-03-06 | 2024-03-15 | 10 | Sarah Lee | In Progress | 75
PMT-003 | Risk Assessment | 2024-03-16 | 2024-03-20 | 5 | Michael Brown | Not Started | 0
PMT-004 | Resource Allocation | 2024-03-21 | 2024-03-28 | 8 | Emily Chen | Planned | 0
PMT-005 | Development Phase | 2024-03-29 | 2024-04-15 | 27 | Team A | Not Started | 0