## Worksheet
Task | Start Date | End Date | Duration | Progress (%) | Responsible | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 days | 95% | Maria Rodriguez | On Track
Requirements Gathering | 2024-01-16 | 2024-02-15 | 30 days | 75% | James Wilson | On Schedule
Design Phase | 2024-02-16 | 2024-03-31 | 56 days | 50% | Sarah Kim | In Progress
Development | 2024-04-01 | 2024-06-30 | 91 days | 35% | Team A | On Track
Testing & Quality Assurance | 2024-07-01 | 2024-08-15 | 56 days | 10% | Lena Thomas | Delayed
Deployment & Launch | 2024-08-16 | 2024-09-30 | 45 days | 0% | David Lee | Not Started