## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Progress (%)
PMT-001 | Project Initiation | 2024-03-01 | 2024-03-15 | 15 | John Doe | Completed | 100
PMT-002 | Requirements Gathering2024-03-16 | 2024-04-10 | 35 | Jane Smith | In Progress | 65
PMT-003 | Design Phase | 2024-04-11 | 2024-05-15 | 35 | Mike Johnson | Not Started | 0
PMT-004 | Development Phase | 2024-05-16 | 2024-07-31 | 75 | Sarah Lee | Not Started | 0
PMT-005 | Testing Phase | 2024-08-01 | 2024-08-31 | 31 | David Brown | Not Started | 0
PMT-006 | Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | Lisa Wang | Not Started | 0