## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies | Progress (%) | Milestone? | Priority | Resource Allocation
P-001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | Maria Santos | Completed | - | 100 | Yes | High | Project Manager, Stakeholder Team
P-002 | Requirements Gathering & Analysis | 2024-03-16 | 2024-04-10 | 35 | David Kim | In Progress | P-001 | 60 | No | High | Business Analysts, End Users
P-003 | Design Phase (UI/UX) | 2024-04-11 | 2024-05-15 | 45 | Lena Torres | Not Started | P-002 | 0 | No | Medium | Design Team, UX Researchers
P-004 | Development & Coding | 2024-05-16 | 2024-08-31 | 127 | James Reed | Not Started | P-003 | 0 | No | High | Full Dev Team, QA Support
P-005 | Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 65 | Sophia Patel | Not Started | P-004 | 0 | No | High | QA Engineers, Test Managers
P-006 | Deployment & Go-Live | 2024-10-16 | 2024-10-31 | 16 | Robert Chen | Not Started | P-005 | 0 | Yes | Critical | IT Operations, Cloud Team
P-007 | Post-Launch Review & Documentation | 2024-11-01 | 2024-11-30 | 30 | Elena Martinez | Not Started | P-006 | 0 | No | Medium | Documentation Team, Support Staff