## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Employee | Status | Progress (%)
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Jane Doe | Completed | 100%
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | John Smith | In Progress | 65%
Design Phase | 2024-04-11 | 2024-05-15 | 45 | Lisa Chen | Not Started | 0%
Development Phase | 2024-05-16 | 2024-07-15 | 60 | Mike Brown | Not Started | 0%
Testing & QA | 2024-07-16 | 2024-08-30 | 45 | Sarah Lee | Not Started | 0%
Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | David Kim | Not Started | 0%
Post-Deployment Review | 2024-09-16 | 2024-09-30 | 15 | Jane Doe | Not Started | 0%