## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 days | Sarah Chen | Completed
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 days | James Reed | In Progress
Design Phase | 2024-04-11 | 2024-05-15 | 45 days | Lisa Park | Planned
Development Phase | 2024-05-16 | 2024-07-31 | 76 days | Mike Thompson | Not Started
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 days | Emma Wright | Not Started
Deployment & Launch | 2024-09-01 | 2024-09-15 | 15 days | David Kim | Planned
Post-Launch Support | 2024-09-16 | 2024-10-31 | 46 days | Rachel Gomez | Not Started