## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Project Manager | On Track
Scope Definition | 2024-03-16 | 2024-04-05 | 21 | Business Analyst | In Progress
Requirements Gathering | 2024-04-06 | 2024-05-10 | 35 | Requirements Team | Planned
Design Phase | 2024-05-11 | 2024-06-30 | 61 | Design Lead | Not Started
Development Phase | 2024-07-01 | 2024-11-30 | 150 | Engineering Team | Planned
Testing & QA | 2024-12-01 | 2025-01-31 | 62 | QA Manager | Not Started
Deployment & Go-Live | 2025-02-01 | 2025-02-15 | 15 | IT Operations | Planned
Post-Implementation Review | 2025-02-16 | 2025-03-03 | 18 | Project Manager | Not Started