## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Completed | 100%
Requirements Gathering | 2024-01-16 | 39In Progress | 75%
Design Phase | 2024-02-15 | 47Planned | 0%
Development Phase | 2024-04-01 | 91Not Started | 0%
Testing & QA | 2024-07-01 | 45Not Started | 0%
Deployment & Go-Live | 2024-08-16 | 16Not Started | 0%
Post-Launch Support | 2024-09-01 | 122Not Started | 0%