## Worksheet
Task | Start Date | End Date | Duration (Months) | Status | Responsible
Project Initiation | 2024-01-01 | 2024-01-31 | 1 | Completed | Project Manager
Requirements Gathering | 2024-02-01 | 2024-03-31 | 2 | In Progress | Business Analysts
Design Phase | 2024-04-01 | 2024-05-31 | 2 | Planned | Design Team
Development Phase | 2024-06-01 | 2024-10-31 | 5 | Scheduled | Development Team
Testing & Quality Assurance | 2024-11-01 | 2024-12-31 | 2 | Pending | QA Team
Deployment & Go-Live | 2025-01-01 | 2025-01-31 | 1 | Not Started | IT Operations
Post-Deployment Review | 2025-02-01 | 2025-02-28 | 1 | Planned | Project Manager