## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | J. Smith | Completed
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | A. Johnson | In Progress
Design Phase | 2024-04-11 | 2024-05-15 | 45 | M. Davis | Pending Start
Development Phase | 2024-05-16 | 2024-07-31 | 77 | L. Brown | Not Started
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 | T. Wilson | Planned
Deployment & Training | 2024-09-01 | 2024-09-30 | 30 | S. Garcia | Not Started
Post-Implementation Review | 2024-10-01 | 2024-10-15 | 15 | R. Martinez | Pending Start