## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | John Smith | Completed
Requirements Gathering | 2024-01-16 | 2024-02-28 | 43 | Sarah Lee | In Progress
Design Phase | 2024-03-01 | 2024-04-15 | 65 | Mike Johnson | Not Started
Development | 2024-04-16 | 2024-07-31 | 116 | Team A | Not Started
Testing & QA | 2024-08-01 | 2024-09-15 | 65 | Lisa Chen | Not Started
Deployment & Launch | 2024-09-16 | 2024-09-30 | 15 | Alex Brown | Not Started
Post-Launch Support | 2024-10-01 | 2024-12-31 | 90 | Support Team | Not Started