## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 days | John Smith | On Track
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 days | Sarah Lee | On Track
Design Phase | 2024-04-11 | 2024-05-15 | 45 days | Mike Chen | In Progress
Development | 2024-05-16 | 2024-07-31 | 76 days | Team A | Scheduled
Testing & QA | 2024-08-01 | 2024-09-15 | 65 days | Lisa Wong | Not Started
Deployment & Training | 2024-09-16 | 2024-10-31 | 46 days | Robert Brown | Planned