## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | John Smith | Completed
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Sarah Lee | In Progress
Design Phase | 2024-04-11 | 2024-05-30 | 60 | Mike Johnson | Planned
Development Phase | 2024-06-01 | 2024-08-31 | 90 | Team A | Not Started
Testing & QA | 2024-09-01 | 2024-10-15 | 55 | Lisa Brown | Not Started
Deployment & Launch | 2024-10-16 | 2024-10-31 | 16 | Alex Chen | Not Started
Post-Launch Review | 2024-11-01 | 2024-11-15 | 15 | All Team Members | Planned