## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 days | Project Manager | On Track
Requirements Gathering | 2024-01-16 | 2024-02-15 | 30 days | Business Analysts | On Track
Design Phase | 2024-02-16 | 2024-03-31 | 46 days | UI/UX Team | On Track
Development | 2024-04-01 | 2024-06-30 | 91 days | Development Team | On Track
Testing & Quality Assurance | 2024-07-01 | 2024-08-15 | 45 days | QA Team | On Track
Deployment & Training | 2024-08-16 | 2024-09-30 | 45 days | Operations & Training Team | On Track
Post-Implementation Review | 2024-10-01 | 2024-10-15 | 15 days | Project Manager & Stakeholders | On Track