## Worksheet
Task Name | Start Date | End Date | Durations (Days) | Responsible Person | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Jane Smith | Completed
Milestone: Requirements Finalized | 2024-01-20 | 2024-01-20 | 1 | John Doe | Completed
Design Phase (UI/UX) | 2024-01-21 | 2024-02-15 | 35 | Sarah Lee | In Progress
Milestone: Prototype Approved | 2024-02-16 | 2024-02-16 | 1 | Mark Tan | Pending Review
Development Phase (Frontend) | 2024-02-17 | 2024-04-15 | 60 | Alex Kim | Not Started
Development Phase (Backend) | 2024-02-17 | 2024-04-30 | 75 | Linda Wu | Not Started
Milestone: System Integration Complete | 2024-04-30 | 2024-04-30 | 1 | Raj Patel | Pending Review
Testing & QA Phase | 2024-05-01 | 2024-05-31 | 31 | Karen Zhao | Not Started
Deployment & Go-Live | 2024-06-01 | 2024-06-15 | 15 | Tony Green | Not Started
Milestone: Project Closure | 2024-06-16 | 2024-06-16 | 1 | Samantha Clark | Not Started