## Worksheet
Task | Start Date | End Date | Status | Duration (Days)
Project Initiation | 2024-01-01 | 2024-01-15 | Completed | 15
Requirement Gathering | 2024-01-16 | 2024-02-15 | In Progress | 30
Design Phase | 2024-02-16 | 2024-03-31 | Pending | 46
Development | 2024-04-01 | 2024-06-30 | Pending | 91
Testing & Quality Assurance | 2024-07-01 | 2024-08-15 | Pending | 45
Deployment & Go-Live | 2024-08-16 | 2024-08-31 | Pending | 16
Post-Launch Review | 2024-09-01 | 2024-09-15 | Pending | 15