## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible | Status
Project Kickoff & Planning | 2024-03-01 | 2024-03-15 | 15 | Alex Rivera | On Track
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 | Jordan Lee | In Progress
Product Design & Wireframing | 2024-04-11 | 2024-05-05 | 35 | Mia Chen | Pending
Development Phase (Frontend) | 2024-05-06 | 2024-06-15 | 40 | David Kim | Not Started
Development Phase (Backend) | 2024-06-16 | 2024-07-30 | 45 | Sam Patel | Not Started
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 | Taylor Reed | On Track
User Training & Go-Live | 2024-09-01 | 2024-09-30 | 30 | Nina Foster | Pending