## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status | Dependencies
Project Initiation | 2024-03-01 | 2024-03-07 | 7 | Project Lead Team | Completed | None
Requirements Gathering | 2024-03-08 | 2024-03-25 | 18 | Business Analysis Team | In Progress | Project Initiation
Design Phase | 2024-03-26 | 2024-04-15 | 21 | Design Team | Planned | Requirements Gathering
Development Phase | 2024-04-16 | 2024-06-15 | 61 | Development Team | Not Started | Design Phase
Testing & QA | 2024-06-16 | 2024-07-10 | 35 | QA Team | Not Started | Development Phase
Deployment & Launch | 2024-07-11 | 2024-07-15 | 5 | Operations Team | Not Started | Testing & QA
Post-Launch Review | 2024-07-16 | 2024-07-20 | 5 | Project Review Team | Not Started | Deployment & Launch