## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Jane Smith | Completed
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | John Doe | In Progress
Design Phase | 2024-04-11 | 2024-05-15 | 35 | Alice Johnson | Planned
Development Phase | 2024-05-16 | 2024-07-31 | 76 | Team A (Dev) | Not Started
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 | Bob Wilson | Scheduled
Deployment & Go-Live | 2024-09-01 | 2024-09-15 | 15 | Carol Lee | Not Started
Post-Deployment Review | 2024-09-16 | 2024-09-30 | 15 | Jane Smith | Planned