## Worksheet
Task | Start Date | End Date | Duration | Status | Progress (%) | Responsible Person
Project Initiation | 2024-01-01 | 2024-01-15 | 15 days | Completed | 100% | Sarah Johnson
Requirements Gathering | 2024-01-16 | 2024-02-15 | 30 days | In Progress | 65% | Mike Chen
Design Phase | 2024-02-16 | 2024-03-31 | 56 days | Not Started | 0% | Linda Patel
Development | 2024-04-01 | 2024-06-30 | 91 days | Not Started | 0% | David Kim
Testing & QA | 2024-07-01 | 2024-08-15 | 56 days | Not Started | 0% | Emma Taylor
Deployment | 2024-08-16 | 2024-08-31 | 16 days | Not Started | 0% | Robert White