## Worksheet
Date | Task | Priority | Status | Estimated Time (min) | Actual Time (min) | Progress (%) | Dependencies | Owner | Notes
2024-04-01 | Define Project Scope | High | Completed | 60 | 55 | 90% | Stakeholder Review | Jane Doe | Final scope approved by PMO.
2024-04-03 | Develop Project Plan | High | In Progress | 120 | 60 | 50% | Scope Definition, Resource List | John Smith | Waiting on budget sign-off.
2024-04-05 | Conduct Stakeholder Workshops | Medium | Planned | 90 | 0 | 0% | Project Plan Finalized | Lisa Chen | Confirm dates with stakeholders.
2024-04-07 | Assign Roles & Responsibilities | High | Not Started | 45 | 0 | 0% | Project Plan Complete | Michael Lee | Team input required for role clarity.
2024-04-09 | Review Risk Assessment | Medium | In Progress | 75 | 30 | 40% | Scope & Timeline Defined | Sarah Kim | Identified three key risks; mitigation strategies drafted.