## Worksheet
Project Name | Project Manager | Start Date | End Date | Budget (USD) | Status | Priority | Risk Level | Milestone Timeline
Website Redesign | Sarah Johnson | 2024-03-01 | 2024-06-30 | $50,000 | On Track | High | Medium | Q2 Launch, UX Testing (Week 8)
Mobile App Development | Michael Chen | 2024-04-05 | 2025-01-31 | $120,000 | Planning | Critical | High | Beta Testing (Q3), Launch (Q4)
Customer Onboarding Platform | Lisa Rodriguez | 2024-05-10 | 2024-08-31 | $75,000 | In Progress | Medium | Low | Feature Delivery (Weeks 4–6), Review (Week 8)
ERP System Migration | David Kim | 2024-06-01 | 2024-09-30 | $250,000 | At Risk | High | Critical | Phase 1 (Weeks 2–4), Backup Plan in Progress