## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Remarks
Project Kickoff Meeting | John Doe | 2024-03-01 | 2024-03-01 | Completed | 100% | All stakeholders aligned.
Scope Definition | Jane Smith | 2024-03-02 | 2024-03-10 | In Progress | 75% | Final approval pending from Legal.
Resource Allocation | Michael Brown | 2024-03-11 | 2024-03-15 | Pending | - | Team availability confirmed.
Risk Assessment | Sarah Lee | 2024-03-16 | 2024-03-20 | Not Started | - | Initial risk list drafted.
Project Timeline Finalization | David Kim | 2024-03-21 | 2024-03-31 | Not Started | - | To be reviewed by PMO.