## Worksheet
Project Name | Team Members | Status | Start Date | End Date | Progress (%) | Next Milestone | Issues/Concerns | Action Items
Website Redesign | Alex Johnson, Sam Lee, Taylor Reed | On Track | 2024-04-01 | 2024-05-31 | 85% | Launch beta version by May 15 | Design feedback delay from client | Finalize UI mockups by April 20
Mobile App Development | Jordan Wu, Maya Patel, Liam Chen | On Track | 2024-03-15 | 2024-06-30 | 60% | Complete user authentication module by May 1 |  | Integrate payment gateway by May 15
Marketing Campaign Launch | Nina Garcia, Chris Moore | Delayed | 2024-04-10 | 2024-06-15 | 35% | Finalize campaign content by May 5 | Client requires additional creative revisions | Reschedule meeting with client on April 25
Internal System Audit | David Kim, Sophie Tran | In Progress | 2024-04-05 | 2024-05-15 | 50% | Complete risk assessment by May 1 | Limited access to legacy databases | Coordinate with IT team for data access