## Worksheet
Expense Category | Description | Budgeted Amount ($) | Actual Amount ($) | Variance ($) | Variance % | Status
Project Planning | Feasibility studies, scope definition, stakeholder analysis | 15,000.00 | 14,250.00 |  | -750 | -5.0% | On Track
Resource Allocation | Hiring, training, team deployment | 30,000.00 | 32,100.00 | +2,100.00 | +7.0% | Over Budget
Software Development | Development, testing, iteration cycles | 120,000.00 | 118,500.00 | -1,500.00 | -1.25% | On Track
Communication & Meetings | Weekly stand-ups, client reviews, progress reports | 10,000.00 | 11,250.00 | +1,250.00 | +12.5% | Over Budget
Contingency & Risk Management | Unplanned risks, mitigation activities | 20,000.00 | 18,750.00 | -1,250.00 | -6.25% | Under Budget
Training & Knowledge Transfer | Staff onboarding and system training | 8,000.00 | 7,500.00 | -500 | <-6.25% | Under Budget
Total Budgeted: |  |  | 183,000.00 | 174,950.00 | -8,050.00 | -4.4%