## Worksheet
Project ID | Project Name | Start Date | End Date | Status | Assigned Team Member | Budget (USD) | Current Progress (%) | Next Milestone
PM-001 | Website Redesign | 2024-03-15 | 2024-06-30 | On Track | Sarah Johnson | 15,000 | 75% | Launch MVP by May 15
PM-002 | Mobile App Development | 2024-04-01 | 2024-11-30 | In Progress | Michael Chen | 50,000 | 45% | User Testing by July 10
PM-003 | Customer Onboarding System | 2024-05-10 | 2024-12-15 | Planning | Lena Torres | 30,000 | 10% | Finalize Requirements by June 30
PM-004 | Data Analytics Platform | 2024-06-01 | 2025-03-31 | Pending Approval | David Kim | 80,000 | 0% | Budget Review by May 15