## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%) | Notes
Project Initiation | Jane Smith | 2024-03-15 | Completed | Low | 100% | All stakeholders onboarded.
Scope Definition | Mike Johnson | 2024-03-25 | In Progress | Medium | 65% | Final approval pending from PMO.
Resource Allocation | Sarah Lee | 2024-04-05 | Not Started | High | 0% | Team members assigned in next meeting.
Risk Assessment | David Brown | 2024-03-30 | Completed | Low | 100% | Key risks documented and mitigated.
Timeline Development | Lisa Chen | 2024-04-10 | In Progress | Medium | 40% | Milestones defined; Gantt chart being updated.