## Worksheet
Project Name | Project Owner | Start Date | End Date | Status | Budget (USD) | Current Progress (%) | Next Milestone
Website Redesign | Jane Doe | 2024-03-01 | 2024-06-30 | On Track | 15,000 | 75% | Launch Phase (May 15)
CRM Implementation | Mark Smith | 2024-04-10 | 2024-07-31 | In Progress | 25,000 | 45% | User Training (June 1)
Marketing Campaign | Lisa Brown | 2024-05-01 | 2024-08-31 | Planned | 8,500 | 0% | Strategy Finalized (May 20)
Office Relocation | David Lee | 2024-06-01 | 2024-09-30 | Pending Approval | 35,000 | 10% | Site Selection (June 25)