## Worksheet
Project Phase | Budget Allocation (USD) | Duration (Months) | Scheduled Start Date | Scheduled End Date | Responsible Team | Status
Initiation | $25,000 | 2 | Jan 2024 | Mar 2024 | Project Office | On Track
Planning & Feasibility | $50,000 | 4 | Apr 2024 | Aug 2024 | Strategy Team | In Progress
Design & Development | $150,000 | 8 | Sep 2024 | May 2025 | Engineering Team | Planned
Testing & Validation | $40,000 | 6 | Jun 2025 | Dec 2025 | QA Team | Pending Approval
Deployment & Launch | $30,000 | 2 | Jan 2026 | Feb 2026 | Operations Team | Not Started
Post-Implementation Review | $10,000 | 3 | Mar 2026 | May 2026 | Project Office | Planned