## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Risk Level
Project Initiation | John Doe | 2024-01-01 | 2024-01-15 | Completed | 100% | Low
Requirements Gathering | Jane Smith | 2024-01-16 | 2024-02-15 | In Progress | 75% | Moderate
Design Phase | Michael Brown | 2024-02-16 | 2024-03-31 | Pending Approval | 30% | High
Development & Testing | Sarah Lee | 2024-04-01 | 2024-06-30 | Not Started | - | Medium
Deployment & Go-Live | David Kim | 2024-07-01 | 2024-07-31 | Planned | - | Low
Post-Launch Review | Emma Watson | 2024-08-01 | 2024-08-31 | Not Started | - | Low