## Worksheet
Date | Task Description | Responsible Person | Status | Priority | Estimated Time (hrs) | Actual Time (hrs) | Remarks
2024-01-15 | Routine inspection of HVAC systems | John Smith | Completed | Medium | 4 | 3.5 | All systems functioning normally.
2024-02-03 | Review of maintenance schedule for Q1 | Jane Doe | In Progress | High | 2 | - | Updating due dates and responsibilities.
2024-03-10 | Replacement of faulty electrical outlets | Mike Johnson | Completed | High | 3 | 3 | All outlets tested and operational.
2024-04-05 | Quarterly safety compliance audit | Sarah Lee | Scheduled | High | 5 | - | Pending approval from HR and Safety Officer.