## Worksheet
Date | Task Description | Assigned To | Status | Priority | Estimated Completion Time | Actual Completion Time | Notes
2023-10-03 | Inspect HVAC system in Building B | John Smith | Completed | High | 2023-10-04 14:00 | 2023-10-04 15:30 | No issues found; system running efficiently.
2023-10-04 | Update maintenance schedule for elevators | Sarah Lee | In Progress | Medium | 2023-10-06 10:00 |  | Waiting on final floor plan approval.
2023-10-05 | Replace light fixtures in West Wing | Mario Rodriguez | Pending Approval | Low | 2023-10-07 09:00 |  | Procurement pending; cost estimate reviewed.
2023-10-06 | Conduct safety audit of storage area | Linda Park | Not Started | High | 2023-10-08 16:00 |  | New fire extinguisher locations to be verified.