## Worksheet
Project Phase | Objective | Timeline (Days) | Responsible Party | Key Deliverables | Risk Assessment | Status
Initiation | Define project scope, stakeholders, and goals. | 7 | Project Sponsor | Scope Statement, Stakeholder Register | Low | On Track
Planning | Develop detailed work breakdown, schedule, and budget. | 21 | Project Manager | Work Breakdown Structure (WBS), Project Schedule, Budget Forecast | Medium | In Progress
Execution | Implement project activities and manage team. | 60 | Project Team | Delivered Milestones, Team Outputs, Quality Reports | High | Scheduled
Monitoring & Control | Track progress, manage changes, and ensure quality. | 45 | Project Manager & QA Team | Performance Reports, Change Logs, Risk Register Updates | Medium | Pending Review
Closing | Formally close the project and document lessons learned. | 10 | Project Sponsor & Manager | Final Report, Closure Documentation, Lessons Learned Summary | Low | Not Started