## Worksheet
Project Phase | Task Name | Responsible Person | Start Date | End Date | Status | Progress (%) | Risk Level
Initiation | Define Project Scope | John Smith | 2024-03-15 | 2024-03-20 | Completed | 100% | Low
Planning | Create Work Breakdown Structure (WBS) | Anna Lee | 2024-03-21 | 2024-04-05 | In Progress | 65% | Medium
Execution | Team Recruitment & Onboarding | Marcus Brown | 2024-04-06 | 2024-04-15 | Not Started | 0% | High
Monitoring & Control | Weekly Performance Review | Sophia Chen | 2024-04-16 | 2024-05-31 | Completed | 100% | Low
Closure | Final Deliverables Approval | David Kim | 2024-06-01 | 2024-06-10 | Planned | 0% | Medium