## Worksheet
Month | Project Phase | Key Activities | Responsible Team | Timeline (DD/MM/YYYY) | Milestones | Budget Allocation ($)
January | Project Initiation | Feasibility study, Stakeholder identification, Scope definition | Project Steering Committee | 01/01/2024 – 31/01/2024 | Finalize project charter | 50,000.00
February | Planning & Design | Work breakdown structure (WBS), Risk assessment, Resource planning | Project Management Office (PMO) | 01/02/2024 – 28/02/2024 | Complete WBS and risk register | 75,000.00
March | Design Development | Prototype development, Stakeholder reviews, Design validation | Engineering & Design Team | 01/03/2024 – 31/03/2024 | Design sign-off by stakeholders | 85,000.00
April | Development & Testing | Build MVP, Unit testing, Integration testing | Development Team | 01/04/2024 – 30/04/2024 | MVP released for alpha test | 120,000.00
May | Testing & Feedback | User acceptance testing (UAT), Bug fixing, Performance optimization | Quality Assurance & UX Team | 01/05/2024 – 31/05/2024 | Final UAT approval received | 60,000.00
June | Deployment Planning | Training schedules, Go-live plan, Backup & recovery strategy | Operations & Support Team | 01/06/2024 – 30/06/2024 | Deployment readiness checklist approved | 45,000.00
July | Go-Live & Launch | System deployment, User onboarding, Live monitoring setup | Operations & Support Team | 01/07/2024 – 31/07/2024 | System launched successfully | 35,000.00
August | Post-Launch Review | Performance review, User feedback collection, Issue tracking | Project Steering Committee | 01/08/2024 – 31/08/2024 | Final project review report submitted | 25,000.00
September | Optimization Phase | Process improvement, Feature enhancements, Cost review | Product Improvement Team | 01/09/2024 – 30/09/2024 | First optimization roadmap approved | 30,000.00
October | Scale & Expand | Market expansion planning, New feature rollout | Marketing & Growth Team | 01/10/2024 – 31/10/2024 | New markets launched in pilot phase | 70,000.00
November | Compliance & Audit | Data privacy review, Regulatory compliance check, Internal audit | Legal & Compliance Team | 01/11/2024 – 30/11/2024 | All audits passed with no findings | 55,000.00
December | Year-End Review & Planning | Full-year performance report, Budget vs. actuals, 2025 roadmap planning | Project Steering Committee | 01/12/2024 – 31/12/2024 | Annual report and budget plan approved | 60,000.00