## Worksheet
Project Phase | Task Name | Assigned To | Start Date | End Date | Status | Progress (%)
Initiation | Project Scope Definition | Sarah Johnson | 2024-03-15 | 2024-03-25 | Completed | 100%
Planning | Resource Allocation | Michael Chen | 2024-03-26 | 2024-04-10 | In Progress | 75%
Execution | Development Phase | Team Lead - Alex Rivera | 2024-04-11 | 2024-06-30 | Not Started | 0%
Monitoring & Control | Risk Assessment Review | Elena Torres | 2024-05-01 | 2024-05-31 | Scheduled | 0%
Closure | Final Delivery & Sign-Off | Client Representative | 2024-07-15 | 2024-07-31 | Not Started | 0%