## Worksheet
Date | Project Phase | Task Name | Responsible Person | Estimated Time (hrs) | Status | Progress (%) | Dependencies | Notes
2024-04-01 | Planning | Scope Definition Workshop | Jane Doe | 4 | Completed | 100% | None | All stakeholders aligned on project goals.
2024-04-05 | Design | Wireframe Development | John Smith | 8 | In Progress | 60% | Scope Definition Workshop | Review with UX team scheduled for 04-07.
2024-04-10 | Development | Frontend Implementation | Alex Chen | 16 | Not Started | 0% | Wireframe Development Complete | Waiting for design approval.
2024-04-15 | Testing | User Acceptance Testing | Sarah Lee | 12 | Not Started | 0% | Frontend Implementation Complete | Schedule with clients for 04-18.
2024-04-20 | Deployment | Production Launch | Mike Rodriguez | 6 | Planned | 0% | User Acceptance Testing Complete | Launch after final client sign-off.